## Proposed Changes
Change ID | Section | Title | Priority | Severity | Area Affected | What Exists Now | What Documentation Requires | Why This Is a Problem | Recommended Change | Expected Impact | Approval (Yes/No/Modify) | Your Comments / Instructions
P0 — CRITICAL CHANGES (Must Fix)
CHG-01 | C-01 | Add Task Type + Subtype + Process Family | P0-Critical | Critical | Task Data Model | Generic functionType (18 types) with no formal task type tied to documented process families | 32 distinct task types in 17 process families, each with unique workflows, steps, dependencies, SLA rules | Cannot route through process-specific workflows, enforce dependencies, or display process-specific views | Add taskType enum (32 values), taskSubtype (Standard/Mass/Express/Sensitive), processFamily (17 values) | Foundation for all process-specific features
CHG-02 | C-03 | Add Client / Employee / Contract ID Fields | P0-Critical | Critical | Task Data Model | Tasks have requesterName only — no client org, employee ref, or contract ID | Client (lookup), Employee (lookup), Contract ID (string) as core fields per Section G4 | Cannot track per client (hypercare), per employee (lifecycle), or per contract. Reporting impossible. | Add clientId, clientName, employeeId, employeeName, contractId fields | Enables hypercare flagging, per-client SLA, per-contract tracking
CHG-03 | C-04 | Implement 5-Tier SLA Model | P0-Critical | Critical | SLA Framework | SLA per functionType with 18 different values. No named tiers. Single timer. | 5 tiers: Hypercare (2h/4h/12h), Urgent (4h/6h/24h), Priority (8h/12h/48h), Standard (18h/18h/72h), Batch (24h/24h/5BD). Separate FRT/NRT/TPT. | Hypercare clients get generic 24h SLA instead of 2h FRT. FRT/NRT/TPT conflated. | Add slaTier enum; separate slaFRT, slaNRT, slaTPT timers; auto-assign tier | Fixes SLA accuracy; closes 88.5% vs 99% hypercare gap
CHG-04 | C-06 | Add Dependency Enforcement Engine | P0-Critical | Critical | Workflow Logic | Tasks independent — no blocking, no dependency checking | Redline: Legal MUST NOT close before HRX marks Ready. Amendment→Termination: must resolve first. Onboarding→Countersign: auto-check 4 conditions. | Employees NEVER receive agreements when dependency breaks. Single most important workflow fix. | Add blockedBy, dependsOn fields; blocking rules on transitions; auto-block with notification | Prevents critical process breakdowns in Section F
P1 — HIGH PRIORITY CHANGES
CHG-05 | C-12 | Add Current Step / Workflow Stage Tracking | P1-High | High | Task Data Model | 4 statuses (new/in_progress/waiting/resolved) — generic and flat | currentStep enum per process (Awaiting Legal, Awaiting Client, Processing, Awaiting Deposit, Ready for EA Send) | Cannot tell WHERE in 7-step onboarding a task is stuck. Waiting is ambiguous. | Add currentStep with process-specific step values; step-based SLA | Enables pipeline views, bottleneck identification
CHG-06 | D-01 | Add Onboarding Hub View | P1-High | High | Navigation / Views | Single flat My Queue for all tasks | Onboarding Hub: pipeline, EA status, compliance doc tracker, start date tracker, mass onboarding | Country owners cannot see onboarding pipeline separately. No process-specific dashboards. | New nav module with onboarding-specific views, filters, KPIs | Primary documented module per Section G3
CHG-07 | D-02 | Add Offboarding Hub View | P1-High | High | Navigation / Views | Single flat My Queue for all tasks | Offboarding Hub: pipelines, day X of 6 progress, cost calculator, SLA flags | No offboarding pipeline. Cannot track 6-day target. No cost calculator. | New nav module with offboarding-specific views | Primary documented module per Section G3
CHG-08 | D-03 | Add Active EOR Hub View | P1-High | High | Navigation / Views | Single flat My Queue for all tasks | Active EOR Hub: amendments, redlines with dependency enforcement, time off, benefits, verification letters | Amendments/redlines mixed with all tasks. No redline dependency visibility. | New nav module with Active EOR-specific views | Primary documented module per Section G3
CHG-09 | C-08 | Add Hypercare Flag + Hypercare Console | P1-High | High | Task Model + Views | No hypercare concept. All tasks equal. | isHypercare boolean; Console with client health, SLA by client, check-in tracker, entry/exit criteria | Enterprise hypercare (15-20/quarter) get standard SLA. 88.5% vs 99% target. | Add isHypercare flag; client tier lookup; Hypercare Console; auto-elevate SLA | Closes hypercare SLA gap
CHG-10 | C-07 | Add Automation Status + Automation Center | P1-High | High | Task Model + Views | No indication if task is manual/AI/automated | automationStatus enum; Automation Center with AKAI/Zalos, coverage %, hours saved | 71% onboarding automation invisible. Cannot track ROI. | Add automationStatus field; Automation Center nav module | Enables automation ROI tracking
CHG-11 | C-11 | Add Backup Owner + OOO Auto-Assignment | P1-High | High | Task Assignment | assigneeId only. No backup owner. | backupOwner field auto-assigned on OOO. Auto-redirect per Section G6. | Manual OOO toggling causes ticket assignment failures — flagged as critical. | Add backupOwnerId; OOO status; auto-redirect logic | Eliminates OOO-related ticket drops
CHG-12 | C-10 | Add Sensitive Task Flag | P1-High | High | Access Control | No sensitivity classification | sensitiveFlag boolean restricting visibility for terminations per G4 | Sensitive termination data visible without task-level restriction. | Add isSensitive flag; visibility filtering in PermissionsContext | Protects sensitive employee data
CHG-13 | C-16 | Add Country Owner Assignment + PAM Routing | P1-High | High | Ownership / Assignment | Members have region/team but no country assignment. No auto-routing. | Country-owner model: each country has designated HRX owner. PAM routes by country. | Auto-assignment by country is HRX foundation. Without it, manual routing required. | Add countryAssignments to member; PAM-like routing | Automates core task routing
P2 — MEDIUM PRIORITY CHANGES
CHG-14 | D-05 | Add Pre-Sales Support Module | P2-Medium | Medium | Navigation / Views | No pre-sales view/workflow | Pre-Sales module: feasibility requests, country readiness, benefits guidance, intake form | No formalized pre-sales process — major gap per documentation. | New nav module with intake form, SLA, CSM coordination | Formalizes #hrx-pre-sales-workflow
CHG-15 | C-20 | Add Resolution Notes Field | P2-Medium | Medium | Task Data Model | Internal notes only, no structured resolution docs | resolutionNotes text for outcome documentation per G4 | No way to document resolution. Knowledge lost. | Required resolutionNotes on resolve; enforce before closing | Captures institutional knowledge
CHG-16 | C-13 | Add AI Summary Field | P2-Medium | Medium | Task Data Model | No AI summary on tasks | aiSummary text with 2-3 sentence auto-generated summary per G4 | Agents must read full history for context. | Add aiSummary field; populate via AI on create/update | Reduces context-loading time
CHG-17 | C-18 | Implement 4-Tier Progressive Auto-Escalation | P2-Medium | Medium | Workflow Logic | escalation_auto_route setting exists but no progressive logic | 75%→warning; 90%→alert+TL; breach→RM; 2x breach→SWAT per G6 | Escalation manual. SLA breaches not auto-escalated. | Implement 4-tier logic; configurable thresholds | Reduces ~40% breach rate
CHG-18 | C-19 | Add Function Manager Overlay | P2-Medium | Medium | Ownership Model | 4 roles only (Admin, Regional Mgr, Team Lead, Agent) | Three-layer: Country Owner + Function Manager + Regional Manager per G7 | Function managers invisible. Cannot route exceptions. | Function manager per process family; visibility in hub views | Completes documented ownership model
P3 — LOW PRIORITY CHANGES
CHG-19 | E-04 | Align Task Sources to Documentation | P3-Low | Low | Task Data Model | 15 sources incl bamboohr, greenhouse, notion | Zendesk, Workbench, Jira (legacy), Slack, Platform | 10 undocumented sources add noise. | Trim to documented; add Platform; keep others configurable | Cleaner source reporting
CHG-20 | E-02/03 | Remove / Fix Mock Data (KB + Litigation) | P3-Low | Low | Knowledge Hub / Slack | 50 hardcoded KB entries; 8 mock litigation cases | Real integration or proper empty states | Mock data misleading in production. | Remove mocks; show coming-soon states | Sets honest expectations

## Future Improvements
ID | Improvement | Rationale | Approval (Yes/No/Modify) | Your Comments
FUT-01 | Real-time WebSocket Updates | Queue requires manual refresh. At 70K+ monthly workflows, real-time essential.
FUT-02 | Task Merge Capability | Duplicate tickets across Zendesk/Jira/Workbench flagged in docs. Need merge.
FUT-03 | SLA Pause/Resume for External Dependencies | Awaiting Legal/client should not count against HRX SLA.
FUT-04 | Predictive SLA Risk Scoring | AI prediction of which tasks will breach based on history.
FUT-05 | Mobile-Responsive Design | 24/7 SWAT team needs mobile for urgent escalations.
FUT-06 | Scheduled Auto-Reports | Weekly/monthly auto-reports to leadership. Currently manual.
FUT-07 | Client Self-Service Portal | Clients forced through L1 — direct channel for hypercare.
FUT-08 | Payroll Cutoff Calendar Integration | Country-specific cutoffs in SLA calculation.

## Assumptions to Validate
ID | Assumption | Risk if Wrong | Validation Method | Confirmed? (Yes/No/TBD) | Your Comments
ASM-01 | 18 functionType values can be replaced with 32 documented task types | Medium — existing data depends on current types | Review with HRX leadership
ASM-02 | Process hubs needed as separate nav modules (not queue filters) | Medium — could be filter tabs instead | User research with country owners
ASM-03 | 5-tier SLA model replaces per-function model entirely | High — some may need both | Validate with ops leadership
ASM-04 | Country owner assignment is static (not dynamic/seasonal) | Medium — some countries share owners | Check PAM config rules
ASM-05 | Sensitive tasks fully hidden (not just masked) | Medium — privacy implications differ | Check with Legal/Compliance
ASM-06 | Automation Center is admin-only view | Low — may need function mgr access | Validate with Zalos/AKAI owners
ASM-07 | 4-status model coexists with process-specific steps | Low — likely yes | Technical spike
ASM-08 | Mass operation triggers create Slack channels from Ops Hub | High — Slack API permissions needed | Check integration scope

## What Matches Well
Area | Documentation Requirement | Current Build Status | Notes
Morning Briefing | Daily snapshot: open tasks, SLA, team capacity | BriefingView: health score, SLA metrics, team performance, priority tasks, activity feed | Strong match
My Queue | Personal task mgmt with unified SLA, priority sorting | Queue: filters, SLA badges, priority sorting, source indicators, detail panel | Strong match
Escalation Workflow | Severity levels with auto-routing and SLA per severity | 4 levels (30m/60m/120m/240m), chain tracking | Strong match
Analytics | SLA%, throughput, escalation rate, response time, scorecards | AnalyticsView: all KPIs + date range + region filters | Strong match
Knowledge Hub | SOPs, country guides, playbooks, FAQ | KnowledgeHubView: search, policies, runbooks, tools, FAQ, country resources | Structure matches; content mock
Comms & Announcements | Team comms with types and acknowledgment | CommsView: 5 types, ack tracking, drafts, reminders | Strong match
GM Reporting | Country KPIs, queue health, escalation patterns | GMReportingView: country/team breakdown, SLA, CSV export | Strong match
Team Management | Hierarchy, capacity, OOO tracking | TeamView: expandable hierarchy, SLA health, parental leave | Good match
Access Control | Role-based permissions | 4 roles, 15 views, 20 actions, data scoping | Comprehensive
Settings | SLA config, notifications, escalation rules | 100+ settings across 21 categories | Very thorough
Calendar | Events, deadlines, leave tracking | CalendarView: month/week, event types, start dates | Good match
Projects | Process improvement tracking | ProjectsView: types, statuses, priorities, progress, linked tasks | Good match
Slack Integration | Slack escalation visibility | SlackView: escalation tab, AI suggested reply | Partial match
Source Tracking | Multi-system origin | 15 source types tracked per task | Exceeds requirement