## All Zaps
Zap # | Category | Zap Name | Direction | Priority | Trigger (When) | Trigger App | Action (Then Do) | Action App | Data Mapped | Why You Need This | Notes / Dependencies
ZENDESK INBOUND
ZAP-01 | Zendesk Inbound | New Zendesk Ticket → Create Ops Hub Task | Inbound → Ops Hub | P0-Launch Day | New ticket created in Zendesk (HRX group) | Zendesk | POST /api/v1/webhooks/zendesk — creates task in Ops Hub queue with source=zendesk | Ops Hub API | ticket_id → externalId, subject, description, requester_name, requester_email, assignee_email → assigneeId, priority, tags, country (from custom field), created_at → sourceCreatedAt | Core inbound flow — every Zendesk ticket appears in My Queue automatically | Filter: only HRX group tickets. Map Zendesk priority to Ops Hub priority.
ZAP-02 | Zendesk Inbound | Zendesk Ticket Updated → Update Ops Hub Task | Inbound → Ops Hub | P0-Launch Day | Ticket updated in Zendesk (status change, new comment, assignee change) | Zendesk | PATCH /api/v1/tasks/:id/status — sync status changes back to Ops Hub | Ops Hub API | ticket_id → lookup task by externalId, status mapping (open→new, pending→waiting, solved→resolved), assignee_email, latest_comment | Keeps Ops Hub in sync when agents work directly in Zendesk | Use Zendesk trigger "Ticket Updated" with conditions. Map statuses: open→new, pending→waiting, solved→resolved.
ZAP-03 | Zendesk Inbound | Zendesk SLA Breach → Create Ops Hub Alert | Inbound → Ops Hub | P1-Week 1 | Zendesk SLA target breached (FRT or NRT) | Zendesk | POST /api/v1/tasks/:id/escalate — auto-escalate breached task in Ops Hub | Ops Hub API | ticket_id → task lookup, breach_type (FRT/NRT), breach_time, assignee | SLA breaches in Zendesk auto-trigger escalation in Ops Hub — no manual monitoring needed | Requires Zendesk Professional+ for SLA triggers.
ZENDESK OUTBOUND
ZAP-04 | Zendesk Outbound | Ops Hub Task Resolved → Solve Zendesk Ticket | Outbound → External | P0-Launch Day | Task status changed to "resolved" in Ops Hub | Ops Hub API (webhook) | Update ticket status to "Solved" in Zendesk | Zendesk | task.externalId → ticket_id, resolutionNotes → internal_note, resolved_by → assignee | Agents resolve in Ops Hub → Zendesk auto-closes. Single source of truth. | Send resolution notes as internal note on Zendesk ticket.
ZAP-05 | Zendesk Outbound | Ops Hub Task Reassigned → Update Zendesk Assignee | Outbound → External | P1-Week 1 | Task assignee changed in Ops Hub | Ops Hub API (webhook) | Update assignee on Zendesk ticket | Zendesk | task.externalId → ticket_id, new_assignee_email → assignee | Assignment stays in sync — no dual-updating in both systems | Lookup Zendesk user by email to get agent ID.
ZAP-06 | Zendesk Outbound | Ops Hub Note Added → Add Zendesk Internal Note | Outbound → External | P2-Week 2-3 | Internal note added to task in Ops Hub | Ops Hub API (webhook) | Add internal note/comment to Zendesk ticket | Zendesk | task.externalId → ticket_id, note.body → comment_body (internal=true), note.authorName | Notes written in Ops Hub appear in Zendesk — agents never need to switch tabs to add notes | Only sync internal notes, not all activity.
WORKBENCH INBOUND
ZAP-07 | Workbench Inbound | New Workbench Task → Create Ops Hub Task | Inbound → Ops Hub | P0-Launch Day | New task created in Workbench | Workbench (webhook/API) | POST /api/v1/webhooks/zendesk — creates task with source=workbench | Ops Hub API | wb_task_id → externalId, task_type → functionType, subject, country, assignee, priority, created_at | Core inbound flow — Workbench is primary task system. Every WB task must appear in Ops Hub. | Workbench is internal — may need custom webhook or scheduled poll instead of Zapier trigger.
ZAP-08 | Workbench Inbound | Workbench Task Status Change → Update Ops Hub | Inbound → Ops Hub | P0-Launch Day | Workbench task status updated | Workbench (webhook/API) | PATCH /api/v1/tasks/:id/status — sync status to Ops Hub | Ops Hub API | wb_task_id → lookup by externalId, new_status → mapped status, updated_at | Two-way sync keeps both systems current | Map Workbench-specific statuses to Ops Hub 4-status model.
SLACK INBOUND
ZAP-09 | Slack Inbound | Slack Urgent Assist Message → Create Escalation | Inbound → Ops Hub | P0-Launch Day | New message posted in #hrx-urgent-assist channel | Slack | POST /api/v1/escalations — create escalation with source=slack, severity based on keywords | Ops Hub API | message_text → subject + description, user → escalated_by, timestamp, channel, thread_ts → slack_thread_link | Urgent assists from Slack auto-appear in Escalations view — no copy/paste needed | Parse message for ticket links (ZD-XXXXX patterns). Auto-link to existing task if found.
ZAP-10 | Slack Inbound | Slack Reaction (🚨) on Message → Create Alert | Inbound → Ops Hub | P2-Week 2-3 | Specific emoji reaction added to message in HRX channels | Slack | POST /api/v1/escalations — create escalation from flagged message | Ops Hub API | reaction → severity mapping (🚨=critical, ⚠️=high, 👀=medium), message_text, user, channel, permalink | Team can flag urgent items with emoji → auto-creates escalation | Configure which channels to watch. Map emoji to severity levels.
SLACK OUTBOUND
ZAP-11 | Slack Outbound | SLA Breach → Slack Alert to Team Lead | Outbound → External | P0-Launch Day | Task SLA reaches 90% or breaches in Ops Hub | Ops Hub API (webhook) | Post formatted alert to team lead via Slack DM or channel | Slack | task.subject, task.assignee, task.slaStatus, task.country, sla_remaining_mins, task.url (deep link) | Team leads get instant Slack notification when tasks approach or breach SLA — matches documented escalation logic (90% → alert + TL) | Include deep link back to Ops Hub task. Use Block Kit for rich formatting.
ZAP-12 | Slack Outbound | Escalation Created → Slack Notification to Manager | Outbound → External | P0-Launch Day | New escalation created in Ops Hub | Ops Hub API (webhook) | Post escalation alert to relevant Slack channel + DM to assigned manager | Slack | escalation.subject, severity, source, task_link, escalated_by, sla_deadline | Managers notified immediately of new escalations without checking Ops Hub | Route to #hrx-urgent-assist for critical, team channel for high/medium.
ZAP-13 | Slack Outbound | Daily Morning Briefing → Slack Summary | Outbound → External | P1-Week 1 | Scheduled: Every weekday at 8:00 AM (per region timezone) | Schedule (Zapier) | GET /api/v1/tasks (filtered) → format and post summary to #hrx-daily-briefing | Slack | open_count, breached_count, at_risk_count, new_overnight, top_priority_tasks (top 5), team_capacity | Team gets a daily digest in Slack without opening Ops Hub — matches Briefing view | Three zaps needed: EMEA (8am CET), APAC (8am SGT), AMER (8am EST). Use Zapier schedule trigger.
ZAP-14 | Slack Outbound | Task Resolved → Post Resolution to Thread | Outbound → External | P2-Week 2-3 | Task with Slack source resolved in Ops Hub | Ops Hub API (webhook) | Reply in original Slack thread confirming resolution | Slack | task.externalId → thread_ts, resolution_notes, resolved_by, time_to_resolve | Closes the loop on Slack-originated escalations — requester sees resolution in thread | Only for tasks with source=slack and a stored thread_ts.
JIRA LEGACY
ZAP-15 | Jira Legacy | Existing Jira Ticket Updated → Update Ops Hub Task | Inbound → Ops Hub | P1-Week 1 | Jira issue status changed (for remaining legacy tickets) | Jira | PATCH /api/v1/tasks/:id/status — sync legacy Jira tickets still in flight | Ops Hub API | jira_key → externalId lookup, status mapping (To Do→new, In Progress→in_progress, Done→resolved), assignee | Legacy Jira tickets still being worked need to sync until fully migrated to Workbench | Sunset this zap once Jira migration complete. Filter to HRX project keys only (HR, OPS).
GOOGLE SHEETS
ZAP-16 | Google Sheets | Country Tracker Row Added → Create Ops Hub Task | Inbound → Ops Hub | P2-Week 2-3 | New row added to country-specific Google Sheet (Japan/Spain/Germany trackers) | Google Sheets | POST /api/v1/tasks — create task from spreadsheet entry | Ops Hub API | row columns → subject, country, priority, assignee, due_date, task_type, notes | Eliminates dual-tracking — country owners add to Sheet, it auto-appears in Ops Hub | One zap per country sheet. Long-term: deprecate sheets entirely once Ops Hub has hub views.
ZAP-17 | Google Sheets | Weekly KPI Export → Append to Reporting Sheet | Outbound → External | P2-Week 2-3 | Scheduled: Every Monday 6:00 AM UTC | Schedule (Zapier) | GET /api/v1/tasks + calculate KPIs → append row to GM Reporting Google Sheet | Google Sheets | week_ending, total_tasks, resolved, open, sla_compliance_pct, avg_resolution_hrs, escalation_count, by_region breakdown | Auto-populates weekly reporting sheet for GM/leadership review | Calculate KPIs server-side or in Zapier code step.
LOOKER / ANALYTICS
ZAP-18 | Looker / Analytics | Looker Alert Triggered → Create Ops Hub Alert | Inbound → Ops Hub | P1-Week 1 | Looker scheduled alert fires (SLA breach rate > threshold, volume spike, etc.) | Looker (email/webhook) | POST /api/v1/announcements — create alert-type announcement in Ops Hub | Ops Hub API | alert_name → title, alert_body → body, dashboard_link → externalRef, severity mapping | Looker anomaly alerts appear in Ops Hub Alerts view — single pane of glass | Looker alerts can send webhooks or emails. Use email parse or webhook trigger.
CALENDAR
ZAP-19 | Calendar | Cal.com Booking Created → Create Calendar Event in Ops Hub | Inbound → Ops Hub | P2-Week 2-3 | New booking on Cal.com (mass onboarding kickoff, hypercare check-in, interview) | Cal.com | POST /api/v1/tasks or create calendar event → appears in Calendar view | Ops Hub API | booking.title, booking.datetime, booking.attendees, booking.type (kickoff/checkin/interview), booking.notes | Mass onboarding kickoffs and hypercare check-ins auto-tracked in Ops Hub Calendar | Cal.com has native Zapier integration. Map booking type to task type.
EMAIL / GMAIL
ZAP-20 | Email / Gmail | Announcement Sent → Email to Team | Outbound → External | P2-Week 2-3 | Announcement status changed to "sent" in Ops Hub | Ops Hub API (webhook) | Send formatted email to target audience (all team / region / individual) | Gmail | announcement.title → subject, announcement.body → email_body, announcement.target → recipient_list, announcement.priority → urgency_flag | Critical announcements reach team via email in addition to Ops Hub — ensures visibility | Build recipient list from members API based on target (all/EMEA/APAC/AMER). Use HTML template.
TASK LIFECYCLE
ZAP-21 | Task Lifecycle | Task Unassigned > 30 min → Auto-Assign to Country Owner | Bidirectional | P1-Week 1 | Scheduled: Every 15 minutes, check for unassigned tasks older than 30 min | Schedule (Zapier) | GET /api/v1/tasks?status=new&assignee=none → lookup country owner → PATCH assign | Ops Hub API | task.country → country_owner_mapping → assigneeId, auto_assign_note | Implements PAM-like auto-routing — no task sits unassigned for more than 30 min | Maintain country→owner mapping in Zapier table or Ops Hub settings. Respect OOO status.
ZAP-22 | Task Lifecycle | Task Waiting > 48h → Auto-Follow-Up Reminder | Bidirectional | P2-Week 2-3 | Scheduled: Every hour, check for waiting tasks older than 48h | Schedule (Zapier) | POST /api/v1/tasks/:id/notes — add auto-reminder note + Slack DM to assignee | Ops Hub API + Slack | task.id, task.subject, waiting_since, assignee → Slack DM | Prevents tasks from going stale in "waiting" status — auto-nudge after 48h | Only nudge once (check for existing auto-reminder note). Configurable threshold.
ZAP-23 | Task Lifecycle | Escalation Unresolved > SLA → Auto-Escalate Up | Bidirectional | P1-Week 1 | Scheduled: Every 10 minutes, check escalations past SLA deadline | Schedule (Zapier) | PATCH /api/v1/escalations/:id — bump escalation level (TL→RM→SWAT) + notify | Ops Hub API + Slack | escalation.id, current_level, sla_deadline, next_level → update + Slack notification to next-level manager | Implements 4-tier auto-escalation: TL → RM → SWAT → Leadership per documentation G6 | Critical for matching documented escalation logic. Check escalation chain to determine next level.
MASS OPERATIONS
ZAP-24 | Mass Operations | Mass Onboarding Detected (4+ tasks same client) → Create Slack Channel | Outbound → External | P2-Week 2-3 | Scheduled: Every hour, check for 4+ new onboarding tasks from same client in 24h | Schedule (Zapier) | Create Slack channel #mass-onboard-{client} + invite relevant members + post summary | Slack | client_name, task_count, country_list, assignee_list → channel_name, channel_topic, initial_message | Documentation requires auto-channel creation for mass onboarding (4+ EORs per client) | Check if channel already exists before creating. Add function manager (Beatriz) automatically.
ZAP-25 | Mass Operations | Mass Offboarding Detected (5+ terminations/week) → Alert + Assign PM | Outbound → External | P2-Week 2-3 | Scheduled: Every Monday, check for 5+ termination tasks from same client in past 7 days | Schedule (Zapier) | Create Slack channel + DM function manager (Insiya) + create project in Ops Hub | Slack + Ops Hub API | client_name, termination_count, countries, → channel, project with milestones, PM assignment | Documentation requires dedicated PM + Slack channel within 24h for mass offboarding 2.0 | Per documentation C2: 5+ active EOR terminations/week triggers mass offboarding process.
REPORTING
ZAP-26 | Reporting | Weekly SLA Compliance Report → Slack + Sheet | Outbound → External | P1-Week 1 | Scheduled: Every Friday 5:00 PM UTC | Schedule (Zapier) | GET metrics → format report → post to #hrx-gm-reporting + append to Google Sheet | Slack + Google Sheets | sla_compliance_by_region, by_team, by_function, escalation_rate, top_breached_countries, automation_savings | Leadership gets weekly performance report without manual compilation | Use Zapier Code step to calculate metrics from API responses.
ZAP-27 | Reporting | Monthly Team Scorecard → Email to Regional Managers | Outbound → External | P2-Week 2-3 | Scheduled: 1st of every month, 9:00 AM UTC | Schedule (Zapier) | GET full month metrics → generate HTML scorecard → email to RMs | Gmail | agent_name, tasks_completed, sla_pct, avg_resolution_time, escalation_rate, AISAT_score per agent | Matches documentation C17 Performance Management KPI tracking — automated monthly scorecards | Include comparison to previous month. Flag agents below 90% SLA.
HYPERCARE
ZAP-28 | Hypercare | Hypercare Client Task Created → Auto-Elevate SLA | Bidirectional | P1-Week 1 | New task created where client is on hypercare list | Ops Hub API (webhook) | PATCH /api/v1/tasks/:id — set slaTier=hypercare, isHypercare=true, notify dedicated TL | Ops Hub API + Slack | task.clientId → hypercare_client_list lookup → isHypercare=true, slaTier=hypercare, dedicated_tl → Slack DM | Hypercare client tasks automatically get priority SLA (2h FRT vs 18h standard) per documentation G5 | Maintain hypercare client list in Zapier table. Update when clients enter/exit hypercare program.
ZAP-29 | Hypercare | Weekly Hypercare Check-In Reminder → Slack + Calendar | Outbound → External | P2-Week 2-3 | Scheduled: Every Monday 9:00 AM, for each active hypercare client | Schedule (Zapier) | Post reminder to dedicated TL via Slack DM + create Cal.com booking link | Slack | client_name, tl_name, tl_slack_id, last_checkin_date, open_tasks_count, sla_compliance_pct | Ensures weekly check-ins happen per documentation C9 Hypercare Enterprise requirements | Skip if check-in already scheduled this week.
COMPLIANCE
ZAP-30 | Compliance | Payroll Cutoff Approaching → Alert Country Owner | Outbound → External | P1-Week 1 | Scheduled: Daily check — 3 days before each country payroll cutoff | Schedule (Zapier) | DM country owner via Slack with open tasks that need resolution before cutoff | Slack | country, cutoff_date, days_remaining, open_amendment_count, open_onboarding_count, owner_slack_id | Prevents missed payroll deadlines per documentation C6 — country-specific cutoff awareness | Maintain country cutoff calendar (e.g., Spain: 10th amendments, 15th new hires, 19-22 payment).
ZAP-31 | Compliance | Compliance Doc Overdue → Escalate + Block Onboarding | Bidirectional | P2-Week 2-3 | Compliance document not received within 5 days of request | Schedule (Zapier) | POST escalation + update task currentStep to "Compliance Blocked" + notify country owner | Ops Hub API + Slack | task.id, employee_name, country, document_type, days_overdue, country_owner | Per documentation C4: 5+ day buffer from month-end needed. Auto-escalate when approaching deadline. | Only for tasks with functionType=compliance or onboarding with compliance step.
TEAM / OOO
ZAP-32 | Team / OOO | Google Calendar OOO Event → Update Member OOO Status | Inbound → Ops Hub | P1-Week 1 | OOO event detected on team member Google Calendar | Google Calendar | PATCH /api/v1/members/:id — set OOO status + trigger backup owner assignment | Ops Hub API | calendar_event → member_email lookup → ooo_start, ooo_end, backup_owner_id (from settings) | Auto-syncs OOO from calendar — eliminates manual toggle per documentation pain point F | Look for events with title containing "OOO", "Out of Office", "PTO", "Vacation", "Leave".
ZAP-33 | Team / OOO | Member Goes OOO → Reassign Open Tasks to Backup | Bidirectional | P1-Week 1 | Member OOO status activated in Ops Hub | Ops Hub API (webhook) | GET tasks assigned to member → PATCH reassign each to backup owner → Slack notify both | Ops Hub API + Slack | member.id → open tasks, backup_owner_id, task_ids → reassign, Slack DMs to both parties | No task left behind when someone goes OOO — implements auto-redirect per documentation G6 | Send summary to backup: "You have X tasks reassigned from {name} while they are OOO until {date}".

## By Priority
Priority | Count | Zap IDs | Summary
P0-Launch Day | 10 | ZAP-01, ZAP-02, ZAP-04, ZAP-07, ZAP-08, ZAP-09, ZAP-11, ZAP-12, ZAP-21, ZAP-28 | Core inbound/outbound sync (Zendesk↔Ops Hub, Workbench→Ops Hub), Slack escalation intake, SLA breach alerts, auto-assignment, hypercare elevation
P1-Week 1 | 9 | ZAP-03, ZAP-05, ZAP-13, ZAP-15, ZAP-23, ZAP-26, ZAP-28, ZAP-30, ZAP-32, ZAP-33 | Zendesk SLA triggers, assignee sync, daily briefing, Jira legacy, auto-escalation, weekly report, payroll cutoff alerts, OOO sync + reassignment
P2-Week 2-3 | 11 | ZAP-06, ZAP-10, ZAP-14, ZAP-16, ZAP-17, ZAP-19, ZAP-20, ZAP-22, ZAP-24, ZAP-25, ZAP-27, ZAP-29, ZAP-31 | Note sync, emoji reactions, Slack thread resolution, Google Sheets import/export, calendar, email announcements, waiting-task nudges, mass ops, monthly scorecards, compliance alerts
P3-Nice to Have | 0 | None yet | All current zaps are P0-P2. P3 items would be cosmetic Slack formatting, advanced Looker integration, etc.

## Setup Checklist
Step | Task | Details | Done?
1 | Create Zapier account / upgrade plan | Need Zapier Professional (/mo) minimum for multi-step zaps, webhooks, and scheduled triggers. Team plan (/mo) if sharing zaps.
2 | Connect Zendesk app in Zapier | Go to Zapier → My Apps → Add Zendesk. Use admin API token. Grant read/write on tickets.
3 | Connect Slack app in Zapier | Add Slack workspace. Grant: channels:write, chat:write, reactions:read, users:read. Install to HRX workspace.
4 | Connect Jira app in Zapier | Add Jira Cloud. Use API token from admin. Filter to HR/OPS projects only.
5 | Connect Google Sheets app in Zapier | Add Google account with access to country tracker sheets (Japan, Spain, Germany).
6 | Connect Google Calendar in Zapier | Add Google account for OOO detection. Needs read access to team calendars.
7 | Connect Gmail in Zapier | Add Gmail for outbound email notifications (announcements, scorecards).
8 | Set up Ops Hub API webhook URL | Your backend runs at localhost:3001. For Zapier, you need a public URL. Use ngrok for dev, real domain for prod.
9 | Create Zapier webhook trigger endpoint | For outbound zaps (Ops Hub → external), set up webhook URLs in Ops Hub Settings → Zapier integration.
10 | Create country→owner mapping table | In Zapier Storage or Google Sheet: country_code, owner_email, backup_email, payroll_cutoff_day.
11 | Create hypercare client list | In Zapier Storage or Google Sheet: client_id, client_name, dedicated_tl_email, tier (enterprise/standard), start_date.
12 | Build P0 zaps first (10 zaps) | Start with ZAP-01 through ZAP-04 (Zendesk), ZAP-07/08 (Workbench), ZAP-09 (Slack), ZAP-11/12 (alerts), ZAP-21 (auto-assign).
13 | Test each zap with real data | Use Zapier test mode. Create a test Zendesk ticket, verify it appears in Ops Hub. Resolve in Ops Hub, verify Zendesk updates.
14 | Turn on P1 zaps (Week 1) | SLA triggers, daily briefing, Jira legacy, auto-escalation, weekly report, OOO sync.
15 | Turn on P2 zaps (Week 2-3) | Note sync, Google Sheets, mass ops, compliance alerts, monthly scorecards.
16 | Monitor Zapier task usage | Check Zapier dashboard weekly. At 70K monthly workflows you may need Zapier Company plan for task volume.